## Sheet1
| Tasks | Assignee | Estimate
FE (UI) | Home Page + NavBar + Footer + Banner + Search Bar + New Jobs + Hot Jobs + Most Salary + Intro | Bảo | 14h
| Sign-in signup candidate signup company | Danh | 2h
| Job Details + Information Company + Information Job | Quân | 8h
| Profile + Form update info - Cadidate: + List CV + List Follow job + List job's applycation - Company: + List Job + CRUD Job + List Follow cadidate | Đức | 16h
| Company Details + Intro company + List Jobs | Quân | 8h
| Search Page + List search job | Bảo | 4h
BE | Create DB using EF Core | Danh | 4h
| Seed test data | Danh | 1h
| CRUD for Candidate | Danh | 2h
| CRUD for Company | Quân | 2h
| Signup | Danh | 2h
| Login | Danh | 2h
| CRUD for CV | Quân | 2h
| CRUD for Job | Bảo | 2h
| CRUD for ApplicationDetail | Đức | 2h
FE(Features) | Update Profile | Danh, Quân
| add and delete CV | Đức
| CRUD job | Bảo
| View all job's application | Đức
| View all candidates applied | Quân
| Apply job | Quân
| Search Job | Bảo
| Favourite jobs | Danh
Method | Api | STT
POST | Sign-in/Sign-up | 1
GET | search | 2
PUT | Edit info cadidate | 11 |  | ApplicationController | 7, 16
DELETE | delete CV | 13
POST | add new CV | 14
GET | Get CV List | 6
POST | Cadidate Apply for Job | 7
POST | Save Job ( optional) | 8 |  | CadidateController | 6, 8, 9, 11, 13, 14, 18
DELETE | delete appliced | 16
GET | detail cadidate | 9 |  | CompanyController | 5, 12, 15, 19, 20, 21
GET | Info company | 10 |  | JobController | 3,4
GET | Company Detail | 5
PUT | Edit info company | 12 |  | AuthenController | 1
GET | get all cadidate through company | 18
GET | Company List | 15
GET | get jobs are saved by cadidate | 17
POST | add new job | 19
PUT | edit job | 20
DELETE | delete job | 21
GET | Job List | 3
GET | Job Details | 4